## PL Other
Aquaculture (PL - Other) Fishery - Schedule of Cost Recoverable Fisheries Regulatory Services |  |  |  |  | Reporting Period: 1/4/15 - 30/9/16
[7 empty] | [Status] | [Status]
2. Compliance Services | [6 empty] | On track | On track | Strategic
Function | Description | Deliverables / Milestones | KPI** | Performance | Traffic light | Comment | Issue | Issue | Operational
2.1 Inspections of licenced or authorised commercial fishers | 2.1.1 Inspections are undertaken at any time in any location to ensure the level of compliance is proven to be at an acceptable level. | Using intelligence, conduct targeted inspections at lease site to ensure compliance with legislation. | Number of inspections for Private Land - Other reported annually. | No. of inspections planned and complete in final report | On track | 1 inspection has been completed | at risk | at risk | Project
| The outcome of this activity maintains or raises a risk perception in the mind of any commercial fisher who is contemplating committing an offence. |  | Type of offences for Private Land - Other reported at end of year (final report). | List of offences and no. of times occurred in final report | [Status]
This leads to maximising voluntary compliance, and creates a deterrent effect.
3. Fisheries Management Services
Function | Description | Deliverables / Milestones | KPI** | Performance | Traffic light | Comment
3.1 Operational management of aquaculture fisheries | 3.1.1 Preparation of briefs and advice papers, and other activities regarding management of aquaculture operations. | Prepare reports, including briefs to senior DEPI management on time as required. | Source and number of reports prepared | No. of reports NIL List of report types N/A | On track | No requests were received
| 3.1.2 Stakeholder services and engagement (e.g. responding to requests for information) – requests are often of a technical and time-consuming nature. | Provide advice and support to licensing on licence applications, variations and conditions within 14 days of receipt of request. | Source and number of requests | No. of requests NIL List of request sources N/A | On track | No requests were received
| 3.1.3 Management of urgent safety issues and (e.g. floods). | Respond to all industry requests or comments within 20 working days. | Number of requests and response time | No. of requests NIL No. timeframe met N/A No. timeframe not met N/A | On track | No requests were received
|  | Work with aquaculture licence holders to facilitate development of a viable aquaculture industry, including development of an aquaculture forum before November. | Activity that promotes development of the aquaculture sector (note this may be across multiple licence classes) | No. and date of industry meetings 1 No. and type of other activities NIL | On track | Held an aquaculture forum in August 2015 and working to advance representation for the sector
|  | Liaise with water authorities, EPA and other agencies on water quality issues as required. | Source and number of issues | List of issues NIL Source of issues N/A Number resolved N/A | On track | No requests were received
|  | Liaise with licence holders, local councils and water authorities as required. | Source and number of liaisons | List of issues NIL Source of issues N/A number resolved N/A | On track | No requests were received
4. Licence Administration Services
Function | Description | Deliverables / Milestones | KPI** | Performance | Traffic light | Comment
4.1 Commercial Catch and Effort | 4.1.1 Operation of the C&E Unit (Monitoring receipt of C&E returns; entering of details in the database; checking accuracy; printing C&E reports as required). | All data entered in the data base within 3 working days of receipt of dockets. | All entries reported with timeframe. | No. of entries 1 No. timeframe not met NIL | On track
|  | All requests for data provided within 5 working days. | Number and source of requests reported. | No. of requests received NIL Source of each request N/A | On track
5. Cost Recovery Administration Services
Function | Description | Deliverables / Milestones | KPI** | Performance | Traffic light | Comment
5.1 Cost recovery administration | 5.1.1 Operational costs only for the provision of secretariat service for the FCRSC (e.g. Chair’s services, meeting room hire, and committee allowances for travel, accommodation and meals). | FCRSC meeting agenda and papers circulated two weeks in advance of meetings. | Meeting dates and minutes reported twice yearly. | FCRSC #38 22nd June, agenda circulated 14/5/15 FCRSC #39 20 August, agenda circulated 5/8/15 - 18/8/15 FCRSC #40 20 October, agenda circulated 1/10/15 | On track
|  | FCRSC minutes prepared and circulated within 7 working days of meetings. | Minutes completed and published. | #38 Minutes circulated 2/7/15, published 28/7/15 #39 Minutes circulated 7/9/15, published 1/12/15 #40 Minutes circulated 28/10/15, published 1/12/15 | On track
| Prospective cost recovery system | Compliance Services | #REF!
|  | Management Services | #REF!
|  | Administration Services | #REF!
|  | Licence Administration | #REF!
|  | Cost Recovery Administration | #REF!
|  | TOTAL | #REF!
|  | Total after small operator concession | 538