## WZ RL
Rock Lobster Western Zone Fishery - Cost Recoverable Fisheries Regulatory Services | [5 empty] | Reporting Period: 1/4/15 - 30/9/16
1. Research Services | [7 empty] | [Status]
Function | Description | Deliverables | KPI** | Traffic light | Performance | Traffic light | Comment | On track | Strategic
1.1 Data collection, monitoring and analysis for stock assessment | 1.1.1 Management of field operations: · Annual fishery independent fixed site survey. · On-board observer program. · In-port sampling. · Puerulus collection & measurement. | Fixed site surveys completed by end of March each year. | Fixed site surveys completed by end of March. |  | No. of survey sites completed 11 Date of completion April 2015 | On track | Procurement for survey vessels in progress. All other monitoring underway. | Issue | Operational
|  | Puerulus data collected and submitted. | Puerulus data submitted in a timely manner (date?) |  | Date of data submission | On track | Completed outside reporting period. Note data collection is continuous (monthly) | at risk | Project
| 1.1.2 Management and analysis of catch & effort data, fishery independent data and puerulus data. | All field data entered, edited and archived in SAS with all processing completed by 30 November. | Processing of field data completed by 30 Nov. |  | No. of data entries and date completed | On track | Completed outside reporting period.
| 1.1.3 Stock assessment modelling to determine annual TACC output. | Peer-reviewed annual fishery status report completed by the end of October. | Peer review completed by 31 Oct. |  | Date peer review completed | On track | Completed
|  | Data report provided to the RLRAG by the end of December. | Report provided to RLRAG by 31 Dec. |  | Date and method data report delivered | On track | Completed outside the reporting period
|  | Ad hoc reports as requested by the Department. | Ad hoc requests completed in a timely manner. |  | No. of requests 1 Date of requests July 2015 | On track | Rock lobster CPUE enquiry completed
|  | Annual stock assessment report completed by the end of February. | Annual stock assessment report completed by 28 Feb. |  | Date and method of delivery | On track | Completed outside the reporting period
|  | Presentation of stock assessment to DEDJTR and RLRAG by the end of February. | Annual stock assessment report completed and presented by 28 Feb. |  | date stock assesment presented | On track | Completed outside the reporting period
|  | All stock assessment analyses and model outputs presented at the TACC workshop (held before the end of April). | Stock asessments and analyses presented at TACC by 30 April |  | Date and method of presentation Powerpoint presentation by SARDI | On track | Workshop date delayed this year into May, but delivered on time in alignment with revised date.
2. Compliance Services
Function | Description | Deliverables | KPI** | Traffic light | Performance | Traffic light | Comment
2.1 Inspections of licenced or authorised commercial fishers | 2.1.1 Inspections are undertaken at any time in any location to ensure compliance. This involves: - Enforcement of size limits. - Enforcement of take-area reporting. - Enforcement of take when allocated quota holding is reached. | Using intelligence, targeted inspections conducted: - at sea, - on land and, - at processor. | Number of inspections for Western Zone Rock Lobster reported annually. |  | No. of inspections planned and complete in final report | On track | 41 on land and 10 on water inspections have been completed
|  |  | Type of offences for Western Zone Rock Lobster reported at end of year (final report). |  | List and frequency of offences for final report | [Status]
3. Fisheries Management Services
Function | Description | Deliverables | KPI** | Traffic light | Performance | Traffic light | Comment
3.1 Setting quota and harvest limits | 3.1.1 Prepare for and participate in the annual TACC advisory forum. | Consult with stakeholders in accordance with statutory requirements prior to setting the annual TACC. | Statutory requirements for consultation met |  | No. of stakeholders Statutory requirements met | On track | Consultation phase conducted 25 March - 24 April
| 3.1.2 Document and distribute a comprehensive summary of the TACC forum outcomes to industry associations. | Hold an annual TACC advisory forum, attended by DEDJTR staff, at which the proposed TACC will be discussed and stakeholder feedback sought. | Forum held with DEDJTR and industry stakeholders |  | Date of forum No. of issues raised Date minutes circulated | On track | Forums 14 May Minutes circulated 22 May
| Prepare the Further Quota Order to set the annual TACC. | Seek comment from stakeholders on the proposed TACC and associated management arrangements including those implemented by Fisheries Notice. | Stakeholder comments recorded |  | No. of issues raised No. of issues managed No. of comments on Fishery Notice | On track | Consultation phase conducted 22 May - 8 June
| 3.1.3 Administration of statutory consultation process related to the Further Quota Order. This includes consideration and review of public submissions. | Public submissions, unless otherwise requested by the submitter, are published on the departmental website before the start of the fishing season. | Submissions published by due date |  | No. of submissions Date published | On track | 2 submissions received
|  | Publish the Further Quota Order setting the TACC along with any necessary Fisheries Notices in the Victoria Government Gazette and notify stakeholders before the start of the fishing season. | Further Quota Order published |  | Date published and source | On track | FQO published 18 June
3.2 Operational management of marine and estuarine fisheries | 3.2.1 Prepare briefs, interpret information, attend meetings and develop discussion papers to inform the fisheries executive and the Minister on issues related to the management of the commercial fishery. | Liaise with DEDJTR business units, the Fisheries Victoria Executive Team and other government agencies to develop and implement legislative and regulatory changes that help to ensure the fishery remains sustainable. | Source and number of meetings reported for 2015. |  | List of meetings No. of meetings | On track | Numerous meetings with stakeholders, including cost recovery reporting and information sessions on the new harvest strategy and management plan
| 3.2.2 Assess, advise on and respond to emerging issues. | Respond to emerging issues in fisheries management. | Issue log reported for 2015 | Operational | List of issues | On track | Issue: Number of coffs per licence
| 3.2.3 Respond to industry queries including requests for information and updates on catch. | Implement Fisheries Notices as required to address emerging management issues in the fishery. | Fishery notices reported for 2015. | Project | List of Fishery Notices | On track | Numerous requests for data and information
| 3.2.4 Consider permit applications for industry research and other activities. | Work with stakeholders to improve on the quality of service delivery. | Targetted improvements identified, delivered and assessed |  | List of improvements identified No. delivered & No. assessed. | On track | No permit applications received
|  | Provide advice regarding general and research permits submitted by industry representative bodies. | Advice provided on permit applications received |  | No. of applications received No. of times advice provided | On track
4. Licence Administration
Function | Description | Deliverables | KPI** | Traffic light | Performance | Traffic light | Comment
4.1 Quota catch recording and administration services | 4.1.1 Operation of the C&E Unit (Monitoring receipt of C&E returns; entering of details in the database; checking accuracy; printing C&E reports as required) | All data entered in the data base within 3 working days of receipt of dockets. | All entries reported with timeframe. |  | No. of entries 426 No. timeframe not met 0 | On track
|  | All requests for rock lobster data provided within 5 working days. | Number and source of requests reported. |  | No. of requests received 20 Source of each request: individuals | On track
| 4.1.2 Administration of fisheries quota accounting (Monitoring and adjustment of quota balances via in-person reporting and IVR). | All quota balances adjusted within 24 hours of receipt of documentation. | All quota balances adjusted within 24 hours of receipt of documentation. |  | No. of quota balances received 21 No. timeframe met 21 | On track
4.1.3 Monitoring and adjustment of quota (follow up on over quota, incomplete reports, and receive calls from fishers when they experience difficulties with IVR).
5. Cost Recovery Administration
Function | Description | Deliverables | KPI** | Traffic light | Performance | Traffic light | Comment
5.1 Cost recovery administration | 5.1.1 Operational costs only for the provision of secretariat service for the FCRSC (e.g. Chair’s services, meeting room hire, and committee allowances for travel, accommodation and meals). | FCRSC meeting agenda and papers circulated at least a week in advance of meetings. | Meeting dates and minutes reported twice yearly. |  | FCRSC #38 22nd June, agenda circulated 14/5/15 FCRSC #39 20 August, agenda circulated 5/8/15 - 18/8/15 FCRSC #40 20 October, agenda circulated 1/10/15 | On track
|  | FCRSC minutes prepared and circulated within 7 working days of meetings. | Minutes completed and published. |  | #38 Minutes circulated 2/7/15, published 28/7/15 #39 Minutes circulated 7/9/15, published 1/12/15 #40 Minutes circulated 28/10/15, published 1/12/15 | On track
| Prospective cost recovery system | Research Services | #REF!
|  | Compliance Services | #REF!
|  | Management Services | #REF!
|  | Administration Services | #REF!
|  | Licence Administration | #REF!
|  | Cost Recovery Administration | #REF!
|  | TOTAL | #REF!
24.19
71
3634