## WPPPB
Western Port / Port Phillip Bay Fishery – Schedule of Cost Recoverable Fisheries Regulatory Services | [5 empty] | Reporting Period: 1/4/15 - 30/9/16
1. Research Services | [7 empty] | [Status]
Function | Description | Deliverables | KPI** | Traffic light | Performance | Traffic light | Comment | On track | Strategic
1.1 Data collection, monitoring and analysis for stock assessment | 1.1.1 Annual catch sampling to determine age and length composition. | Pre-recruit survey data summary for King George whiting provided by 30 April each year. | KGW pre-recruit survey summary provided by 30 April. |  | Date provided Format | On track | Completed by due date. | Issue | Operational
| 1.1.2 Annual pre-recruit surveys and assessment. | Pre-recruit survey data summary for snapper and sand flathead provided by 30 June each year. | Snapper and sand flathead pre-recruit survey summary provided by 30 June. |  | Date provided Format | On track | Completed by due date. | at risk | Project
| 1.1.3 Analysis of all data, including commercial Catch & Effort data and annual workshop information, to determine status of key species and the fishery. | Annual reporting of catch sampling data collected for the fishery to be provided by 31 August each year. | Catch sampling data report provided by 31 August. |  | Date provided Format | On track | Completed in April 2015
|  | Annual reporting of standardised catch and effort fishery data provided by 30 June 2015-19. | Standardised Catch and effort data report provided by 30 June each year. |  | Date provided Format | at risk | Not delivered
|  | Stock assessment workshop conducted for Snapper & KGw every 3 years and 5 years for sand flathead, garfish, calamari & other species. | Snapper and KGW workshop completed by (date) Workshop for other species completed by (date) |  | Date of workshop | at risk | Not completed for KWG, Snapper and Sand flathead
|  | Snapper assessment reports provided by 30 June 2015 and 2018. KGw assessment reports provided by 30 June 2015 and 2017. Sand flathead assessment report provided by 30 June 2015 and 2019. Garfish assessment report provided by 30 June 2016. Calamari assessment report provided by 30 June 2017. Fishery assessment report for other species by 30 June 2016. | Snapper assessment reports provided by 30 June 2015 and 2018. KGw assessment reports provided by 30 June 2015 and 2017. Sand flathead assessment report provided by 30 June 2015 and 2019. Garfish assessment report provided by 30 June 2016. Calamari assessment report provided by 30 June 2017. Fishery assessment report for other species by 30 June 2016. |  | Date provided Format | at risk | KGW, Sand Flathead and Snapper reports not completed.
2. Compliance Services
Function | Description | Deliverables | KPI** | Traffic light | Performance | Traffic light | Comment
2.1 Inspections of licenced or authorised commercial fishers | 2.1.1 Inspections are undertaken at any time in any location to ensure the level of compliance is proven to be at an acceptable level. | Using intelligence, targeted inspections conducted: • at sea, and • at landing, to detect and deter non-compliance with legislation. | Number of inspections for Westernport/Port Phillip Bay reported annually. |  | No. of inspections planned and complete in final report | On track | 13 on land and 6 on water inspections have been completed
| The outcome of this activity maintains or raises a risk perception in the mind of any commercial fisher who is contemplating committing an offence. |  | Type of offences for Westernport/Port Phillip Bay reported at end of year (final report). |  | List of offences and no. of times occurred in final report
This leads to maximising voluntary compliance, and creates a deterrent effect.
3. Fisheries Management Services
Function | Description | Deliverables | KPI** | Traffic light | Performance | Traffic light | Comment
3.1 Operational management of marine and estuarine fisheries | 3.1.1 Prepare briefs, interpret information, attend meetings and develop discussion papers to inform the fisheries executive and the Minister on issues related to the management of the commercial fishery. | Liaise with DEDJTR business units, the Fisheries Victoria Executive Team and other government agencies to develop and implement legislative and regulatory changes that help to ensure the fishery remains sustainable. | Source and number of days of meetings reported for 2015. |  | List of meetings PPB neeting transition No. of meetings 6 | On track | 6- PPB netting buy out meetings
| 3.1.2 Assess, advise on and respond to emerging issues. | Respond to emerging issues in fisheries management. | Issue log reported for 2015 |  | List of issues NIL No. of issues resolved N/A | On track | Not required during this period
| 3.1.3 Respond to industry queries including requests for information and updates on catch. | Implement Fisheries Notices as required to address emerging management issues in the fishery. | Fishery notices reported for 2015. |  | List of Fishery Notices NIL | On track | Not required during this period
| 3.1.4 Consider permit applications for industry research and other activities. | Work with stakeholders to improve on the quality of service delivery. | Targetted improvements identified, delivered and assessed |  | List of improvements identified NIL No. delivered & assessed N/A | On track | Not required during this period
|  | Provide advice regarding general and research permits submitted by industry representative bodies. | Source and number of requests reported |  | No. of requests NIL List of request sources N/A | On track | Not required during this period
4. Licence Administration Services
Function | Description | Deliverables | KPI** | Traffic light | Performance | Traffic light | Comment
4.1 Commercial Catch and Effort | 4.1.1 Operation of the C&E Unit (Monitoring receipt of C&E returns; entering of details in the database; checking accuracy; printing C&E reports as required). | All data entered in the data base within 3 working days of receipt of dockets. | All entries reported with timeframe. |  | No. of entries 252 No. timeframe not met NIL | On track
|  | All requests for WW/PPB Inlet Fishery data provided within 5 working days. | Number and source of requests reported. |  | No. of requests received 27 Source of each request FV21, PRIME1, IND5 | On track
5. Cost Recovery Administration Services
Function | Description | Deliverables | KPI** | Traffic light | Performance | Traffic light | Comment
5.1 Cost recovery administration | 5.1.1 Operational costs only for the provision of secretariat service for the FCRSC (e.g. Chair’s services, meeting room hire, and committee allowances for travel, accommodation and meals). | FCRSC meeting agenda and papers circulated at least a week in advance of meetings. | Meeting dates and minutes reported twice yearly. | Project | FCRSC #38 22nd June, agenda circulated 14/5/15 FCRSC #39 20 August, agenda circulated 5/8/15 - 18/8/15 FCRSC #40 20 October, agenda circulated 1/10/15 | On track
|  | FCRSC minutes prepared and circulated within 7 working days of meetings. | Minutes completed and published. | Project | #38 Minutes circulated 2/7/15, published 28/7/15 #39 Minutes circulated 7/9/15, published 1/12/15 #40 Minutes circulated 28/10/15, published 1/12/15 | On track
| Prospective cost recovery system | Research Services | #REF!
|  | Compliance Services | #REF!
|  | Management Services | #REF!
|  | Administration Services | #REF!
|  | Licence Administration | #REF!
|  | Cost Recovery Administration | #REF!
|  | TOTAL | #REF!
|  |  | Cost recovery administration per licence | 24.19
42