## CZAb
Abalone Central Zone Fishery - Cost Recoverable Fisheries Regulatory Services | [6 empty] | Reporting Period: 1/4/15 - 30/9/16
1. Research Services | [7 empty] | [Status]
Function | Description | Deliverables | KPI** | Traffic light | Performance | Traffic light | Comment | On track | Strategic
1.1 Data collection, monitoring and analysis for stock assessment (Blacklip abalone) | 1.1.1 Objective 1. Monitor commercially important abalone populations and supporting ecosystems. | Complete fishery independent statistical trends in population abundance and size structure. | Fishery independent statistical trends completed by 30 Nov |  | Trend analyses were completed prior to 31 October. | On track | outside reporting period | Issue | Operational
| 1.1.1a) Fishery independent monitoring: annual dive (abundance) surveys to collect data for stock assessment. | Complete fishery dependent statistical trends in catch patterns including changes in catch per unit effort (CPUE). | Fishery dependent statistical trends completed by 30 Nov |  | Trend analyses were completed prior to 30 November. | On track | outside reporting period | at risk | Project
| 1.1.1b) Fishery dependent monitoring: Acquire catch and effort data from the Fisheries Integrated Licensing Systems (FILS) and compile in ABase. | Provide statistical summaries and analytical results that address biological and fishery performance in a spatial management unit (SMU) and zone scales in reports in hardcopy and digital formats. | Statistical summaries provided by 30 Nov |  | Digital and hardcopy sent to Industry EOs on 30 Nov. Bulk printed copies will be available for distribution from 17 Dec 2015. | On track | outside reporting period
| 1.1.2 Objective 2. Assess the sustainability of the current catch of abalone. | Present a brief report summarising the results of analyses undertaken as part of objective 3. | Report presented |  | Written report distributed to Industry representatives on 30 November 2015. | On track | outside reporting period
| 1.1.2a) Analysis of dive survey and catch and effort data to establish TACC at a zonal level. | Compile a periodical stock assessment report that encompasses updated methods, results and conclusions within the context of current management policy and harvest strategy. | Stock assessment compiled |  | Date report delivered to FMS - will be delivered as final draft by 31 Dec 2015. | On track | outside reporting period
| 1.1.2b) Analysis of dive survey and catch and effort data at the scale of specified spatial management units (SMU) to inform harvest strategy recommendations and set optimum catch targets for SMU within the context of an aggregate TACC for zone. |  |  |  | Summaries of cumulative catch performance at SMU scale compared against targets and thresholds provided weekly to Industry. | On track
| 1.1.2c) Database management and reporting to underpin fishery assessments. |  |  |  |  | On track | Ongoing, with substantial modifications made in response to Industry feedback and requests for additional information.
| 1.1.3 Objective 3. Provide information to enable evaluation of harvest strategy options and risks for managing future sustainable production from the commercial dive fishery. | To be agreed pending work harvest strategy | Pending harvest strategy |  | As agreed | On track | outside reporting period
| 1.1.3a) Reef Reports containing abundance trends, length frequencies derived from fishery independent abundance surveys and commercial catch sampling data, and catch, effort, and CPUE extracted from the Fisheries Integrated Licensing System. |  |  |  |  | On track | outside reporting period
| 1.1.3b) Reference point information – compare catches with specified targets, thresholds and limits in the Victorian Abalone Fishery Management Plan (draft). |  |  |  |  | On track | outside reporting period
| 1.1.3c) Present scientific information at Industry Assessment Forums as needed and where appropriate. |  |  |  | Information will be presented during TACC forums in each zone. | On track | outside reporting period
| 1.1.3d) Provide biological advice about emerging issues where relevant to resource resilience and sustainability. |  |  |  |  | On track | Advice provided about: state of stocks in PPB.
1.2 Data collection, monitoring and analysis for stock assessment (Greenlip abalone) | 1.2.1 Analysis of Catch and Effort data to establish TACC at a zonal level. | Provide statistical summaries in the form of Reef Reports to inform decisions and support zone harvest strategies (as required) and pending data availability. | Summaries provided by agreed date |  | See comment | On track | There are only limited current data for CZ, insufficient for analysis.
| 1.2.2 Database management and reporting to underpin stock assessment. |  |  |  | See comment | On track | All greenlip data have been added to database; but insuffcient data to report given 5-fisher rule.
2. Compliance Services
Function | Description | Deliverables | KPI | Traffic light | Performance | Traffic light | Comment
2.1 Inspections of licenced or authorised commercial fishers | 2.1.1 Inspections are undertaken at any time in any location to ensure compliance. This involves: - Enforcement of size limits at the reef code level where there is clear differentiation between reefs (1 by regulation). - Enforcement of take-area reporting. - Enforcement of take when zonal TACC or allocated quota holding is reached. | Using intelligence, targeted inspections conducted: · at sea, · at landing, · in transit, and · at processor. | Number of inspections for Central Zone Abalone reported annually. |  | No. of inspections planned and complete in final report | Issue | 2 on land and 6 on water inspections have been completed. Remainder should be completed during the year.
| Note there is no enforcement of catch limits at finer level than zones. | Integrity of the quota management system maintained. | Type of offences for Central Zone Abalone reported at end of year (final report). |  | List of offences and no. of times occurred in final report | [Status]
3. Fisheries Management Services
Function | Description | Deliverables | KPI | Traffic light | Performance | Traffic light | Comment
3.1 Setting quota and harvest limits | 3.1.1 Provide industry with relevant documentation for the annual TACC advisory forum including printing and distributing reef code report cards and zonal summary report. | Distribute electronic copies of reef code report cards and zonal summary report to industry association 10 working days prior to TACC advisory forum. | Report cards and zonal summary reports distributed electronically 10 days prior to TACC forum |  | Date reef reports and zonal summaries delivered electronically N/A | On track | outside reporting period
| 3.1.2 Assist industry association organise zonal TACC forum including arranging an independent Chair, developing the agenda and arranging travel and accommodation for departmental staff attendance. | Provide hard copies of reef code report cards and zonal summary report to industry associations, quota/licence holders, and fishery operators at the TACC advisory forum. | Report cards and zonal summary reports distributed in hard copy at TACC forum |  | Date reef reports and zonal summaries delivered in hardcopy N/A | On track | outside reporting period
| 3.1.3 Participate in annual TACC advisory forum to engage with industry to set voluntary catch targets at a fine-scale to recommend a zonal TACC. | Ensure annual TACC advisory forum is held in December/January (prior to the start of the fishing season). | TACC advisory forum held before 31 Jan |  | Date of TACC forum N/A | On track | outside reporting period
| 3.1.4 Document and distribute a comprehensive summary of the TACC forum outcomes to industry associations. | Ensure relevant departmental staff attend annual TACC forum. | DEDJTR staff attend TACC forum |  | No. of staff attended N/A | On track | outside reporting period
| 3.1.5 Prepare a Further Quota Order to set the annual TACC. | Provide a draft summary of the TACC forum to industry for comment within 10 working days of the forum. | TACC forum minutes circulated within 10 days |  | Date Minutes circulated N/A | On track | outside reporting period
| 3.1.6 Prepare a Fisheries Notice to set fine-scale minimum size limits. | Publish the Further Quota Order which sets annual TACC in the Victorian Government Gazette by 31 March. | Further Quota Order published by 31 March |  | Date Further Quota Order published N/A | On track | outside reporting period
| 3.1.7 Administer the statutory consultation process related to the Further Quota Order and Fisheries Notice. This includes collating, reviewing and responding to all public submissions. | Publish Fisheries Notice setting fine-scale minimum in the Victorian Government Gazette by 31 March. | Fisheries Notice setting fine-scale minimumpublished by 31 March |  | Date Fishery Notice published N/A | On track | outside reporting period
|  | Publish public Submissions received during consultation on the departmental website by 31 March. | Publice submissions published by 31 March |  | No. of submisisons published and date N/A | On track | outside reporting period
|  | Provide a written response to each public submission within 20 working days of receipt. | Response provided within 10 working days of submission being received |  | No. of responses NIL No. of timeframes not met N/A | On track | outside reporting period
3.2 Operational management of marine and estuarine fisheries | 3.2.1 Prepare briefs, interpret information, attend meetings and develop discussion papers to inform the fisheries executive and the Minister on issues related to the management of the commercial fishery. | Liaise with DEDJTR business units, the Fisheries Victoria Executive Team and other government agencies to develop and implement legislative and regulatory changes that help to ensure the fishery remains sustainable. | Source and number of days of meetings reported for 2015. |  | No. of meetings List of meetings | On track | Numerous meetings including AIC meetings, cost recovery meetings and other general meetings Cost recovery meeting held at Queenscliff in August 2015
| 3.2.2 Assess, advise on and respond to emerging issues. | Respond to emerging issues in fisheries management. | Issue log reported for 2015 |  | List of issues No. of issues resolved | On track | Numerous and ongoing management issues
| 3.2.3 Respond to industry queries including requests for information, updates, and catch and effort data. | Implement Fisheries Notices as required to address emerging management issues in the fishery. | Fishery notices reported for 2015. |  | List of Fishery Notices N/A | On track
| 3.2.4 Consider and respond to permit applications for industry research and other activities. | Work with stakeholders to improve on the quality of service delivery. | Targetted improvements identified, delivered and assessed |  | List of improvements identified N/A No. delivered & assessed N/A | On track | No permit requests
| 3.2.5 Coordinate departmental communication regarding management changes in the central zone abalone fishery (e.g. changing minimum size limits). | Provide advice regarding general and research permits submitted by industry representative bodies. | Source and number of requests reported |  | No. of requests List of request sources | On track | Numerous and ongoing management issues
| 3.2.6 Report on zonal fishery performance (i.e. catch progress against zonal and fine-scale catch targets). | Update DiversWeb to reflect zonal management arrangements by March 31. | DiversWeb updated by March 31. |  | List of updates NIL | On track | No updates required
| 3.2.7 Update DiversWeb to reflect zonal harvest strategy and current catch targets. | Update DiversWeb issues raised by industry within 5 working days. | DiversWeb issues identified |  | List of issues NIL | On track | No issues identified
| 3.2.8 Manage technical issues raised by industry to ensure real-time access to catch information. |  |  |  |  | On track | No technical issues
4. Licence Administration
Function | Description | Deliverables | KPI | Traffic light | Performance | Traffic light | Comment
4.1 Quota catch recording and administration services | 4.1.1 Operation of the C&E Unit (Validations, sourcing price data and providing catch reports). | All abalone price data requests provided within 5 working days. | Abalone price data provided within 5 working days. |  | No. of requests received 3 No. timeframe not met NIL | On track
|  | All requests for abalone data reports provided within 5 working days. | Abalone data reports provided within 5 working days. |  | No. of requests received 17 No. timeframe not met NIL | On track
| 4.1.2 Divers Administration of abalone quota accounting at diver level (ie monitoring and adjustment of quota balances via in-person reporting and IVR, and other support services) for the Central Zone. | All quota balances adjusted within 24 hrs of receipt of required documentation. | Quota balances adjusted within 24 hrs of receipt of required documentation. |  | No. of balances adjusted 3 No. timeframe not met NIL | On track
|  | All data entered in to FILS within 5 working days of receipt of required documentation. | Data entered in to FILS within 5 working days of receipt of required documentation. |  | No. of data entered 318 No. timeframe not met NIL | On track
|  | All catch reports and Quota statements supplied to quota holders within 2 working days of the request. | Catch reports and Quota statements supplied to quota holders within 2 working days of the request. |  | No. of reports supplied 1 No. of statements supplied 1 No. timeframe not met NIL | On track
|  | All monthly catch and statistics reports provided to Abalone Management within 5 working days of the end of the month. | Monthly catch and statistics reports provided to management within 5 working days of the end of the month. |  | No. of timeframes not met NIL | On track
|  | All supplies of Bin Tags, Abalone Docket books, pre-paid envelopes, etc. despatched to divers within 2 working days of request (when supplies on hand). | Bin Tags, Abalone Docket books, pre-paid envelopes, etc. despatched to divers within 2 working days of request (when supplies on hand). |  | No. of timeframes not met NIL No. of tmes supplies not available NIL | On track
|  | Provision of Duty Officer 24 hours per day. | Duty officer provided 24 hours per day |  | Dates service not provided NIL | On track
5. Cost Recovery Administration
Function | Description | Deliverables | KPI | Traffic light | Performance | Traffic light | Comment
5.1 Cost recovery administration | 5.1.1 Operational costs only for the provision of secretariat service for the FCRSC (e.g. Chair’s services, meeting room hire, and committee allowances for travel, accommodation and meals). | FCRSC meeting agenda and papers circulated at least a week in advance of meetings. | Meeting dates and minutes reported twice yearly. | Project | FCRSC #38 22nd June, agenda circulated 14/5/15 FCRSC #39 20 August, agenda circulated 5/8/15 - 18/8/15 FCRSC #40 20 October, agenda circulated 1/10/15 | On track
|  | FCRSC minutes prepared and circulated within 7 working days of meetings. | Minutes completed and published. | Project | #38 Minutes circulated 2/7/15, published 28/7/15 #39 Minutes circulated 7/9/15, published 1/12/15 #40 Minutes circulated 28/10/15, published 1/12/15 | On track
| Prospective cost recovery system | Research Services | #REF!
|  | Compliance Services | #REF!
|  | Management Services | #REF!
|  | Administration Services | #REF!
|  | Licence Administration | #REF!
|  | Cost Recovery Administration | #REF!
|  | TOTAL | #REF!
Cost recovery administration per licence