## Inshore trawl
Trawl Inshore Fishery – Schedule of Cost Recoverable Fisheries Regulatory Services | [5 empty] | Reporting Period: 1/4/15 - 30/9/16
1. Research Services^^ | [7 empty] | [Status]
Function | Description | Deliverables | KPI** | Traffic light | Performance | Traffic light | Comment | On track | Strategic
1.1 Data collection, monitoring and analysis for stock assessment | 1.1.1 Species/fishery specific surveys, projects and assessment. Includes science on biological parameters of species where specifically related to the assessment of sustainable take e.g. aging. Does not include commercial catch and effort collection (see below). | Summarised findings included in stock assessment for snapper every 3 years and non-snapper fishery assessment every 5 years (below). | Stock assessment report delivered by (insert date of next report). |  | Date of report Delivery format | at risk | Snapper assessment report date has been put off until 30 June 2016, due the PPB netting closure issue. | Issue | Operational
|  | Annual reporting of standardised catch and effort fishery data provided by 30 June 2015-2019. | Standardised catch and effort report provided by 30 June 2015 |  | Date and format of report | at risk | Not completed | at risk | Project
|  | Snapper assessment reports provided by 30 June 2015 and 2018. Non-snapper ocean fishery assessment report provided by 30 June 2019. | Snapper assessment report provided by 30 June (2015) Non-snapper report provided by 30 June 2019 |  | Date of report Delivery format Progress work completed | at risk | Snapper assessment report date has been put off until 30 June 2016, due the PPB netting closure issue.
2. Compliance Services
Function | Description | Deliverables | KPI | Traffic light | Performance | Traffic light | Comment
2.1 Inspections of licenced or authorised commercial fishers | 2.1.1 Inspections are undertaken at any time in any location to ensure the level of compliance is proven to be at an acceptable level. | Using intelligence, targeted inspections conducted: • at sea, and • at landing, to detect and deter non-compliance with legislation. | Number of inspections for Inshore Trawl reported annually. |  | No. of inspections planned and complete in final report | Issue | Inspections to be completed during remainder of the year
| The outcome of this activity maintains or raises a risk perception in the mind of any commercial fisher who is contemplating committing an offence. |  | Type of offences for Inshore Trawl reported at end of year (final report). |  | List of offences and no. of times occurred in final report | [Status]
This leads to maximising voluntary compliance, and creates a deterrent effect.
3. Fisheries Management Services
Function | Description | Deliverables | KPI | Traffic light | Performance | Traffic light | Comment
3.1 Operational management of marine fisheries | 3.1.1 Prepare briefs, interpret information, attend meetings and develop discussion papers to inform the fisheries executive and the Minister on issues related to the management of the commercial fishery. | Liaise with DEDJTR business units, the Fisheries Victoria Executive Team and other government agencies to develop and implement legislative and regulatory changes that help to ensure the fishery remains sustainable. | Source and number of days of meetings reported for 2015. |  | List of meetings 1 No. of meetings Cost recovery meeting | On track | Cost recovery meeting held in Lakes Entrance in September 2015
| 3.1.2 Assess, advise on and respond to emerging issues. | Respond to emerging issues in fisheries management. | Issue log reported for 2015 |  | List of issues NIL No. of issues resolved N/A | On track | Not required during this period
| 3.1.3 Respond to industry queries including requests for information and updates on catch. | Implement Fisheries Notices as required to address emerging management issues in the fishery. | Fishery notices reported for 2015. |  | List of Fishery Notices NIL | On track | Not required during this period
| 3.1.4 Consider permit applications for industry research and other activities. | Work with stakeholders to improve on the quality of service delivery. | Targetted improvements identified, delivered and assessed |  | List of improvements identified NIL No. delivered & assessed N/A | On track | Not required during this period
|  | Provide advice regarding general and research permits submitted by industry representative bodies. | Source and number of requests reported |  | No. of requests NIL List of request sources N/A | On track | Not required during this period
4. Licence Administration Services
Function | Description | Deliverables | KPI | Traffic light | Performance | Traffic light | Comment
4.1 Commercial Catch and Effort | 4.1.1 Operation of the C&E Unit (Monitoring receipt of C&E returns; entering of details in the database; checking accuracy; printing C&E reports as required). | All data entered in the data base within 3 working days of receipt of dockets. | All entries reported with timeframe. |  | No. of entries 194 No. timeframe not met NIL | On track | 28 active licences, 26 inactive (yearly nil return)
|  | All requests for Trawl Inshore Fishery data provided within 5 working days. | Number and source of requests reported. |  | No. of requests received 5 Source of each request FV 4, Prime 1 | On track
5. Cost Recovery Administration Services
Function | Description | Deliverables | KPI | Traffic light | Performance | Traffic light | Comment
5.1 Cost recovery administration | 5.1.1 Operational costs only for the provision of secretariat service for the FCRSC (e.g. Chair’s services, meeting room hire, and committee allowances for travel, accommodation and meals). | FCRSC meeting agenda and papers circulated at least a week in advance of meetings. | Meeting dates and minutes reported twice yearly. | Project | FCRSC #38 22nd June, agenda circulated 14/5/15 FCRSC #39 20 August, agenda circulated 5/8/15 - 18/8/15 FCRSC #40 20 October, agenda circulated 1/10/15 | On track
|  | FCRSC minutes prepared and circulated within 7 working days of meetings. | Minutes completed and published. | Project | #38 Minutes circulated 2/7/15, published 28/7/15 #39 Minutes circulated 7/9/15, published 1/12/15 #40 Minutes circulated 28/10/15, published 1/12/15 | On track
^^NB Research services to be confirmed
| Prospective cost recovery system | Research Services | #REF!
|  | Compliance Services | #REF!
|  | Management Services | #REF!
|  | Administration Services | #REF!
|  | Licence Administration | #REF!
|  | Cost Recovery Administration | #REF!
|  | TOTAL | #REF!
|  |  | Cost recovery administration per licence | 24.19
54