## Corner Inlet
Corner Inlet Fishery – Schedule of Cost Recoverable Fisheries Regulatory Services |  |  |  |  | Reporting Period: 1/4/15 - 30/9/16
1. Research Services | [6 empty] | [Status]
Function | Description | Deliverables | Key performance indicator** | Performance | Traffic light | Comment | On track | Strategic
1.1 Data collection, monitoring and analysis for stock assessment. | 1.1.1 Collection of age/length data from sampling of commercial catches of key species (e.g. KG whiting, rock flathead). | Summary of data collected for the fishery to be provided by 31 August each year. | Summary provided by 31 August. | Summary provided | On track | Summary provided April 2015 | Issue | Operational
|  | Assessment for KGW to be held every 3 years and rock flathead and species other than KGW every 5 years. | Assessment of KGW completed by (June 2016). Assessment of rock flathead and other non-KGW species completed by (June 2016) | Date completed Assessment format | On track | Outside reporting period | at risk | Project
|  | Annual reporting of standardised catch and effort fishery data provided by 30 June 2015-2019. | Annual report completed by 30 June each year. | Date provided Format of report | Issue | Draft standardisation report completed for KGW and rock flathead in September 2015 (later than due date of June 2015).
|  | KGW State Assessment report provided by 30 June 2015 and 2017. Garfish assessment report provided by 30 June 2016. | KGW report provided by 30 June 2015. Garfish report provided by 30 June 2016. | Date provided Format of report | at risk | Not delivered. State-wide single species assessments were on-hold during 2015 where there were interactions with the PPB buy out. For garfish, outside reporting period.
|  | Calamari assessment report provided by 30 June 2017. | Calamari report provided by 30 June 2017. | Date provided Format of report | On track | Outside reporting period
|  | Rock flathead and non-KGW assessment report provided by 30 June 2016 | Rock flathead and non-KGW species report provided by 30 June 2018. | Date provided Format of report | On track | Outside reporting period
2. Compliance Services
Function | Description | Deliverables | Key performance indicator | Performance | Traffic light | Comment
2.1 Inspections of licenced or authorised commercial fishers | 2.1.1 Inspections are undertaken at any time in any location to ensure the level of compliance is proven to be at an acceptable level. | Using intelligence, targeted inspections conducted: • at sea, and • at landing, to detect and deter non-compliance with legislation. | Number of inspections for Corner Inlet reported annually. | No. of inspections planned and complete in final report | On track | 5 on land and 6 on water inspections have been completed
| The outcome of this activity maintains or raises a risk perception in the mind of any commercial fisher who is contemplating committing an offence. |  | Type of offences for Corner Inlet reported at end of year (final report). | List of offences and no. of times occurred in final report | [Status]
This leads to maximising voluntary compliance, and creates a deterrent effect.
3. Fisheries Management Services
Function | Description | Deliverables | Key performance indicator | Performance | Traffic light | Comment
3.1 Operational management of marine and estuarine fisheries | 3.1.1 Preparation of briefs and advice papers regarding management of corner inlet fisheries. This includes: | Liaise with DEDJTR business units, the Fisheries Victoria Executive Team and other government agencies to develop and implement legislative and regulatory changes that help to ensure the fishery remains sustainable. | Source and number of days of meetings reported for 2015. | No. of meetings 2 List of meetings: industry meeting, cost recovery meeting | On track | 2 meetings with industry. Cost recovery meeting held in Port Welshpool in September 2015
| providing management advice to the fisheries executive for decision making, including in relation to management controls other than harvest limits e.g. amendments to gear or improved reporting. | Respond to emerging issues in fisheries management. | Issue log reported for 2015 | List of issues 2 No. of issues resolved In progress | On track | Management strategies for Rock Flathead are being developed prior to consultation with relevent stakeholders
| providing services to fishery authority holders e.g. responding to requests for information from fishers, etc. | Implement Fisheries Notices as required to address emerging management issues in the fishery. | Fishery notices reported for 2015. | List of Fishery Notices NIL | On track
| internal coordination to inform external engagement and advice regarding the fishery. | Work with stakeholders to improve on the quality of service delivery. | Targetted improvements identified, delivered and assessed | List of improvements identified 1 Improved process for industry input into the stock assessment process No. delivered & assessed In progress | On track | Improved process for industry input into the stock assessment process
|  | Provide advice regarding general and research permits submitted by industry representative bodies. | Source and number of requests reported | No. of requests NIL List of request sources N/A | On track
4. Licence Administration Services
Function | Description | Deliverables | Key performance indicator | Performance | Traffic light | Comment
4.1 Commercial Catch and Effort | 4.1.1 Operation of the C&E Unit (Monitoring receipt of C&E returns; entering of details in the database; checking accuracy; printing C&E reports as required). | All data entered in the data base within 3 working days of receipt of dockets. | All entries reported with timeframe. | No. of entries 108 No. timeframe not met NIL | On track
|  | All requests for the Corner Inlet Fishery data provided within 5 working days. | Number and source of requests reported. | No. of requests received 9 Source of each request FV 6 PRIME 2 IND 1 | On track
5. Cost Recovery Administration Services
Function | Description | Deliverables | Key performance indicator | Performance | Traffic light | Comment
5.1 Cost recovery administration | 5.1.1 Operational costs only for the provision of secretariat service for the FCRSC (e.g. Chair’s services, meeting room hire, and committee allowances for travel, accommodation and meals). | FCRSC meeting agenda and papers circulated at least a week in advance of meetings. | FCRSC papers provided in a timely manner. | FCRSC #38 22nd June, agenda circulated 14/5/15 FCRSC #39 20 August, agenda circulated 5/8/15 - 18/8/15 FCRSC #40 20 October, agenda circulated 1/10/15 | On track | Meeting no. & date listed Date agenda/paper circulated
|  | FCRSC minutes prepared and circulated within 7 working days of meetings. | FCRSC meeting minutes circulated in a timely manner. | #38 Minutes circulated 2/7/15, published 28/7/15 #39 Minutes circulated 7/9/15, published 1/12/15 #40 Minutes circulated 28/10/15, published 1/12/15 | On track | Date Minutes circulated & published
| Prospective cost recovery system | Research Services | #REF!
|  | Compliance Services | #REF!
|  | Management Services | #REF!
|  | Administration Services | #REF!
|  | Licence Administration | #REF!
|  | Cost Recovery Administration | #REF!
|  | TOTAL | #REF!
|  |  | Cost recovery administration per licence |  | 24.19
18