## Bait General
[Status] | [5 empty] | Reporting Period: 1/4/15 - 30/9/16
On track
Issue | [8 empty] | [Status] | [Status]
at risk | Description | Deliverables | KPI** | Traffic light |  |  |  | Total Rec. ($)* | On track | On track | Strategic
Data collection, monitoring and analysis for stock assessment | NIL | [6 empty] | 0 | Issue | Issue | Operational
2. Compliance Services | [8 empty] | at risk | at risk | Project
Function | Description | Deliverables | KPI** | Traffic light | Performance | Traffic light | Comment | Tot. Rec. ($)*
2.1 Inspections of licenced or authorised commercial fishers | 2.1.1 Inspections are undertaken at any time in any location to ensure the level of compliance is proven to be at an acceptable level. The outcome of this activity maintains or raises a risk perception in the mind of any commercial fisher who is contemplating committing an offence. This leads to maximising voluntary compliance and creating a deterrent effect. | Using intelligence, targeted inspections conducted - at sea, and - at landing, to detect and deter non-compliance with legislation. | Number of inspections for Bait (General) reported annually. |  | No. of inspections planned and complete in final report | On track | 3 on land and 0 on water inspections have been completed | #REF!
|  |  | Type of offences for Bait (General) reported at end of year (final report). |  | List of offences and no. of times occurred in final report | [Status]
3. Fisheries Management Services
Function | Description | Deliverables | KPI** | Traffic light | Performance | Traffic light | Comment | Tot. Rec. ($)
3.1 Operational management of marine and estuarine fisheries | 3.1.1 Preparation of briefs and advice papers regarding management of commercial Bait fisheries. This includes: - providing management advice to the fisheries executive for decision making, including in relation to management controls other than harvest limits e.g. amendments to gear or improved reporting. - providing services to fishery authority holders. - internal coordination to inform external engagement and advice regarding the commercial Bait fishery. | Liaise with DEDJTR business units, the Fisheries Victoria Executive Team and other government agencies to develop and implement legislative and regulatory changes that help to ensure the fishery remains sustainable. | Source and number of days of meetings reported for 2015. |  | No. of meetings 1 List of meetings cost recovery meeting | On track | Cost recovery meeting held in Warrnambool, Queenscliff, Mallacoota and Lakes Entrance in August/September 2015 | #REF!
|  | Respond to emerging issues in fisheries management. | Issue log reported for 2015 | Operational | List of issues NIL No. of issues resolved N/A | On track
|  | Implement Fisheries Notices as required to address emerging management issues in the fishery. | Fishery notices reported for 2015. | Project | List of Fishery Notices NIL | On track
|  | Work with stakeholders to improve on the quality of service delivery. | Targetted improvements identified, delivered and assessed |  | List of improvements identified NIL No. delivered & assessed N/A | On track
|  | Provide advice regarding general and research permits submitted by industry representative bodies. | Source and number of requests reported |  | No. of requests NIL List of request sources NIL | On track
4. Licence Administration
Function | Description | Deliverables | KPI** | Traffic light | Performance | Traffic light | Comment | Tot. Rec. ($)
4.1 Commercial Catch and Effort | 4.1.1 Operation of the C&E Unit (Monitoring receipt of C&E returns; entering of details in the database; checking accuracy; printing C&E reports as required). | All data entered in the data base within 3 working days of receipt of dockets. | All entries reported with timeframe. |  | No. of entries 72 No. timeframe not met NIL | On track |  | #REF!
|  | All requests for Bait General fishery data provided within 5 working days. | Number and source of requests reported. |  | No. of requests received 2 Source of each request FV | On track
5. Cost Recovery Administration Services
Function | Description | Deliverables / Milestones | KPI** | Type | Performance | Traffic light | Comment | Tot. Rec. ($)
5.1 Cost recovery administration | 5.1.1 Operational costs only for the provision of secretariat service for the FCRSC (e.g. Chair’s services, meeting room hire, and committee allowances for travel, accommodation and meals). | FCRSC meeting agenda and papers circulated at least a week in advance of meetings. | Meeting dates and minutes reported twice yearly. |  | FCRSC #38 22nd June, agenda circulated 14/5/15 FCRSC #39 20 August, agenda circulated 5/8/15 - 18/8/15 FCRSC #40 20 October, agenda circulated 1/10/15 | On track |  | #REF!
|  | FCRSC minutes prepared and circulated within 7 working days of meetings. | Minutes completed and published. |  | #38 Minutes circulated 2/7/15, published 28/7/15 #39 Minutes circulated 7/9/15, published 1/12/15 #40 Minutes circulated 28/10/15, published 1/12/15 | On track
| Prospective cost recovery system | Research | 0 |  | * Total Recoverable Cost
|  | Compliance | #REF! |  | ** Key Performance Indicator
|  | Management | #REF! |  | No. of Licences in the Fishery = 12
|  | Licence Administration | #REF! |  | Costs at full implementation in 2016/17
|  | Cost Recovery Administration | #REF!
|  | TOTAL | #REF!
|  | Total after Small Operator concession | 6621
24.19
12